## Iteration 1.2 History
Day | Date | Work | Done | Vel | Left | Finish Date | Over | Bugs
1 | 2010-06-26 | 15.55 | 6.05 | 6.05 | 9.5 | 2010-06-28 | -71.43% | 0 | Planned End | 2010-07-03
2 | 2010-06-27 | 18.75 | 7.9 | 3.95 | 10.85 | 2010-06-30 | -42.86% | 0 | Est. End | 2010-07-03
3 | 2010-06-28 | 18.75 | 7.9 | 2.6333 | 10.85 | 2010-07-03 | 0% | 0 | Est. Overrun | 0%
4 | 2010-06-29 | 18.75 | 7.9 | 1.975 | 10.85 | 2010-07-05 | 28.57% | 0
5 | 2010-06-30 | 18.75 | 7.9 | 1.58 | 10.85 | 2010-07-07 | 57.14% | 0 | Holidays
6 | 2010-07-01 | 18.75 | 7.9 | 1.3167 | 10.85 | 2010-07-10 | 100% | 0
7 | 2010-07-02 | 18.75 | 7.9 | 0.26429 | 10.85 | 2010-08-13 | 585.7% | 0
8 | 2010-07-03 | 11.85 | 11.85 | 0.56429 | 0 | 2010-07-03 | 0% | 0
Formulas:
Finish Date = IF(ISBLANK([Day]),"",IF(AND(NOT(ISBLANK([Finish Date, row above])),[Left, row above]=0),[Finish Date, row above],IF([Vel]=0,"",[Date]+ROUNDUP([Left]/[Vel],0))))
Date = IF(ISBLANK([Day]),"",B8+[Day]-1)

## Iteration 1.2 Graphs
Work remaining (in hours; future data are estimated)
Total estimated work (in man-hours; future data are estimated)
Schedule overrun (future data are estimated)
Open bugs

## Iteration Graph Template (hidden)
Work remaining (in hours; future data are estimated)
Total estimated work (in man-hours; future data are estimated)
Schedule overrun (future data are estimated)
Open work items (TFS bugs and tasks for this iteration)