## Iterations
Stage | Iteration | Description | Status
1 |  | Barebones game | Done
1 | 1 | Barebones display: simple map, console output | Done
1 | 2 | Game engine and hotseat UI: enforcement of game rules with simple interface | Done
2 |  | Simple AI
2 | 1 | Minimax with simple evaluation function
2 | 2 | Improved evaluation function (more strategic considerations)
2 | 3 | Parallelization
3 |  | Game variations
3 | 1 | Starting variations: manual, random, and AI-based territory claiming and population
3 | 2 | Maneuver rules
3 | 3 | Attack rules: overkill
3 | 4 | Card rules: card types, card defense bonuses, tradein values and rules (US vs. EU)
3 | 5 | Objectives: with and without bonuses
3 | 6 | Multiple maps
3 | 7 | Capitals and cities
3 | 8 | Win conditions: dominance, capitals, objectives
3 | 9 | Two-player Risk
3 | 10 | Commander
3 | 11 | Unit limitations
4 |  | Improved UI
4 | 1 | UI abstraction layer (to support multiple technologies)
4 | 2 | Zoomable, scrollable map
4 | 3 | Simple animations
4 | 4 | In-game configuration
4 | 5 | HUD with all elements but simple rendering
5 |  | Networking
5 | 1 | Simple networking
5 | 2 | Dedicated servers / NAT-busting
6 |  | Advanced AI
6 | 1 | Quiescence search
6 | 2 | Singular extensions
6 | 3 | Planning
6 | 4 | Multiple personalities
7 |  | Diplomacy
7 | 1 | Player-to-player text chat
7 | 2 | Diplomacy UI
7 | 3 | Diplomacy AI
8 |  | Polished UI
8 | 1 | Simple sound effects
8 | 2 | Better animations
8 | 3 | More attractive HUD and HUD animations
8 | 4 | Music
8 | 5 | Avatars and other graphics

## Requirements
Stage | Iteration | Feature | Requirement | Description | Status
1 | 1 | Map display | Single map | Displays a single, hardcoded world map. Displays hardware cursor | Done
1 | 1 | Console output | Console output | Ability to write debugging information to a console | Done
1 | 2 | Starting a game | Choosing territories | Click to choose a territory. Displays remaining troop count | Done
1 | 2 | Simple play | Draft stage | Ability to place and remove troops, and commit. Shows current troop count | Done
1 | 2 | Simple play | Attack stage | Click to attack. Ability to change strength, abort, do quick resolution. Ability to move additional troops if victorious | Done
1 | 2 | Simple play | Maneuver stage | Ability to choose source, move troops, cancel or commit | Done
1 | 2 | Simple play | Winning | Detection of end-game state | Done
1 | 2 | Simple play | Cards | Grant star card and trade-in ability if territory was taken. Has simple trade-in UI | Done
2 | 1 | AI | Interface to game and UI | The AI should be able to interface with the game (to play it) and the UI (to give feedback).
2 | 1 | Simple AI | AI claiming and populating | The AI should be able to claim and populate territories intelligently.
2 | 1 | Simple AI | AI drafting | The AI should be able to intelligently decide where to draft armies to protect its interests and facilitate attack.
2 | 1 | Simple AI | AI attacking | The AI should be able to intelligently decide when and where to attack.
2 | 1 | Simple AI | AI maneuvering | The AI should be able to maneuver troops to protect its interests and facilitate attack.
2 | 1 | Simple AI | AI card trading | The AI should be able to decide when to trade cards, and should know the value of gaining cards.

## Tasks
Iteration | Requirement | Task | Original Estimate (man-hours) | Current Estimate (man-hours) | Actual Time |  | Status | 23:37 | 40363.7135 | 17.5073
1.2 |  | Update map loader to support connections between territories | 1.5 | 0.75 | 0.75 | 0 | Done
1.2 |  | Create basic game engine to advance game through its states | 6 | 3 | 3 | 0 | Done
1.2 | 4 | UI for claiming and populating territories | 1 | 1 | 1 | 0 | Done
1.2 | 5 | UI for draft stage | 1 | 0 |  | 0 | Done
1.2 | 6 | UI for attack stage | 2 | 1.5 | 1.5 | 0 | Done
1.2 | 7 | UI for maneuver stage | 1 | 0.2 | 0.2 | 0 | Done
1.2 | 8 | UI for winning | 0.25 | 0.1 | 0.1 | 0 | Done
1.2 | 9 | UI for cards | 6 | 1 | 1 | 0 | Done
1.2 |  | Acquire official rule sets | 1.5 | 1.5 | 1.5 | 0 | Done
1.2 | QA | Fixing bugs | 1 | 1 | 1 | 0 | Done
1.2 | QA | Refactor, polish, and comment code | 4 | 1.8 | 1.8 | 0 | Done
1.2 | - | Totals | 25.25 | 11.85 | 11.85 | 0
2.1 | 10 | Interface AI with game engine | 3 | 3 |  | 3
2.1 | 10 | Interface AI with user interface | 2 | 2 |  | 2
2.1 |  | Implement logging to file | 1 | 1 |  | 1
2.1 | 11 | Develop an evaluation function for claiming and populating | 8 | 8 | 1.5 | 6.5 | Started
2.1 | 11 | Implement minimax search to allow AI to choose territories to claim or populate | 4 | 4 |  | 4
2.1 | 12 | Augment evaluation function and search to support drafting | 2 | 2 | 0.5 | 1.5 | Started
2.1 | 13 | Augment evaluation function and search to support attacking | 3 | 3 | 0.5 | 2.5 | Started
2.1 | 14 | Augment evaluation function and search to support maneuvering | 2 | 2 |  | 2
2.1 | 15 | Augment evaluation function and search to support card gathering and trading | 6 | 6 | 0.5 | 5.5 | Started
2.1 |  | Tune AI | 6 | 6 |  | 6
2.1 |  | Implement genetic algorithm to tune the AI | 6 | 6 |  | 6
2.1 | QA | Document AI strategy | 5 | 5 | 4.5 | 0.5 | Started
2.1 | QA | Fix bugs | 4 | 4 |  | 4
2.1 | QA | Refactor, polish, and comment code | 4 | 4 |  | 4
2.1 | - | Totals | 56 | 56 | 7.5 | 48.5